## Risk Log
ID | Risk | Impact (1-5) | Likelihood (1-5) | Mitigation Strategy | What we will do if this happens | Status | What we did do when it occurred
1 | One of the team members fall ill and are unable to work. | 3 | 4 | Ensure that team members are properly rested and receive medical attention when first signs of illness is spotted. | Review the tasks that was allocated to the ill team member and split the tasks, giving each task to a team members similar roles. | Could Happen
2 | Team member fails to complete given task before set deadline | 3 | 2 | Give strict deadlines for tasks with a detailed timetable to make sure that time is managed properly. | For the first time provide member another day to complete. Spilt task with other members if possible. Set up meeting if it continues to happen and take further action | Could Happen
3 | Someone doesn’t understand something on worksheet | 3 | 4 | In each meeting ask each team member to explain the task at hand to check they understand, if they do not go through the task with them until they gain a full understanding. | Clarify with group members or ask on discussion board. | Could Happen
4 | Lack of communication within team members | 5 | 1 | Ensure that multiple means of communication are set up, for example a Facebook chat and a Slack group chat. | Set up more frequent meetings where everyone discusses how they are getting along with tasks at hand | Could Happen
5 | Disagreement within team members | 5 | 2 | Make sure that everyone has an overall understanding of the task at hand, which will avoid potential disagreements. | Discuss the topic and understand each member’s point of view. Make agreement on the most beneficial point | Could Happen
6 | Team member doesn’t have the relevant knowledge or skill to complete their task | 4 | 2 | Before task is to be completed revise, research and learn the skills required to complete the task. | Ask supervisors for help on where to find resources to learn the skills or proceed to learn through online courses. | Could Happen
7 | Lack of interest or motivation for the project | 4 | 1 | Outline the goal of the project and make sure each team member understands the reward of working as a team to achieve the common goal. | Find out what parts of the project interests them and assign them with those. | Could Happen
8 | Tasks not assigned properly to team members | 4 | 2 | Assess each team members strengths and weaknesses before task allocation, which will ensure the right people are working on the task that best suits them. | Assign tasks that best suits a team member’s skill set. | Could Happen
9 | Tasks are arranged with poor time management | 5 | 2 | Look at the time a task will take to be completed and give divide tasks making sure everyone has similar potential work hours. | A planning poker game could be carried out to determine a relevant time scope by every member for a given task | Could Happen
10 | Difficult to set up meetings that best suits everyone’s schedule. | 2 | 1 | Get weekly availability dates from each team members. | Communicate with every member to set a meeting where everyone’s availability matches | Passed | We discussed all the relevant timings every member can attend and chose the best availability
11 | One of the team member is unhappy with the role allocated to them | 3 | 2 | Assess strengths and weaknesses of team members and allocate a suitable role, which they should enjoy doing as they will be good at it. | Discuss what the member wishes their role to be and assign roles and tasks accordingly. | Could Happen
12 | Someone accidentally loses the source files | 5 | 1 | Make sure that all team members understand git commands and follow a set procedure when committing, pushing etc. | Go through the repository history and select the most recent state. | Could Happen
13 | Unable to find suitable meeting location | 3 | 3 | Organise the meeting location in advance and have a contingency in place. Make sure at least one member brings a laptop so work can be done, without a desktop computer. | Reschedule the meeting if not urgent, or if the meeting is really important set up a Skype meeting. | Passed | Carried out the meeting on slack
14 | Travis build fails | 4 | 5 | Proof read code for potential syntax errors and other potential aspects which will fail the build, before committing. Also run build on remote machine and if tests pass then commit. | Roll back the master and find out what went wrong. | Occurred | Checked what errors occurred and fixed them accordingly
15 | Feature becomes unrealistic to implement | 3 | 2 | Analyse each feature assessing how realistic the feature is to implement, moving any unrealistic requirements to the end of the project, where they may be implemented time permitting. | Give up implementing the feature fully and look for an alternative | Could Happen
16 | Team cannot adapt to change in requirements | 3 | 1 | Ensure team works iteratively in sprints and receive regular feedback from the client | Re-write the users stories affected by the change and come up with alternative stories | Passed | Team were prepared for change in requirements
17 | Spending too much time on additional features, rather than the must features | 5 | 2 | Ensure all 'must' requirements are completed before attempting any others. | Stop implementation and prioritise the must requirements | Could Happen
18 | Team member leaves the group | 5 | 1 | Ensure before the project begins that each member is happy to start the project and willing to see it through to the end. | Allocate the vacated role to another team member and distribute the persons tasks throughout the team | Could Happen
19 | Plagiarism | 5 | 2 | Make sure that each team member produces genuine documentation. If any open source code is used then document it in bibliography | Contact supervisor and the Education Unit at the Student Union. | Could Happen
20 | Product backlog becomes poorly managed and is not updated properly and frequently | 3 | 2 | Ensure that the product back log is updated regularly by allocating two days each week to perform checks on the backlog. | Look over the work that has been completed and backtrack each task, then update the backlog as required. | Passed | Went through the backlog and went through each task and the date added and completed, making the burn down chart clearer and accurate.
21 | Team member reverses history for the master branch on Git Hub without team’s consent | 5 | 1 | Ensure all members are notified before reverting any changes. Make sure all members are regularly staying up to date with the master branch. | We can console the git ref-log | Could Happen
22 | Features being implemented are not fully tested | 5 | 2 | Implement features using Test Driven Development (TDD) and Behaviour Driven Development (BDD). | Fully test the features that have been implemented so far using Cucumber testing. Any further development of new features must be done using TDD and BDD. | Happening | More tests are being carried out on the implemented features
23 | Bad Tests are written for features | 5 | 3 | Ensure that tests implemented pass and feature performs its functionality | Refract test so that it passes and the feature performs the functionality needed. | Could Happen
24 | Team members have to work on individual database server | 3 | 4 | Ensure that all the team members keep up to date with the repository. So that same tables are being created in each member’s database. | Each member will be responsible to stay up to date with the repository so that they can work with same tables in individual databases. | Happening | Each member modified the database configurations accordingly with their credentials. This helped to create same tables on individual databases.
25 | Merge Conflicts | 3 | 4 | Use separate branches for features being developed and continuously pull latest state of repo. | Go though each conflict assessing what has been changed and whiat needs to be kept. | Passed | Went through each file that had a merge conflict and made the appropriate changes.
26 | Client side form validation fails | 5 | 2 | Ensure server side form validation is also implemented. | The server side form validation should take care for client side validation failing | Could Happen
27 | Security restrictions on css | 5 | 3 | Make sure security enables all users to access css resources. | Remove restrictions from accessing css resources | Passed | Followed instructions to remove restrictions from css resources whilst still keeping the application secure
28 | Login with just username and password | 5 | 4 | Include two factor authentication to make it much secure. |  | Passed | Change of requirements introduced two factor authentication as a security measure.

## Notes
ID | A unique ID for the risk
Risk | A description of the risk
Impact | How bad will life be if this happens? 1 = not a big problem 5 = catastrophe
Likelihood | 1 = very unlikey to happen, 5 = probably will happen
What we'll do | How will you respond if the problem occurs?
Status | Could the risk still happen, can't it happen now, is it happening now, did it occur?
You might consider additional columns…
Mitigation strategy
What you actually did